## Vehicle Station Tracker
Vehicle Station Tracker Report
Date: 1/15/2026
Client: TTC
Project: LF76
Fleet Number | VIN | Frame # | Inspector | 01 - Bus Structure Receiving - Nova | 02 - Air Sys components, Steering Column - Nova Air Sys components, Steering Column, Flooring, Engine Insulation | 03 - Air Line Routing, HVAC Piping, Front Ramp | 04 - Elec Harness, Artic Joint | 05 - Rear Shell, Side Panels, Air Test, Eng Comp Electrical | 06 - Fuel Tank, Heat Convectors, Batt Compartment | 07 - Rear Roof, Ext Access Doors, Radiator Piping, Aux Heating | 08 - Front Roof, Trim & Moldings- Nova | 09 - Front Shell, Dash, Engine, Tunnel, Ceiling | 10 - HVAC Roof Units, Axles, Dest Sign - Nova | 11 - Electrical completion & pre-test, Radiator, Roof Gutters | 12 - Handrails, Ext Decals, Baselights, Door Accessories, Coupling of Artic | 13 - Elec & Mech Run-up, Dialysis, Front Door | 14 - Eng Door, Steering Lock, Alignment - Nova | 15 - Windows, Modesty Panels - Nova | 16 - Seats, Rear Doors, Drivers Area - Nova | 17 - Stanchions - Nova | 18 - Under coating, Ext Sign Frames - Nova | 19 - Electrical Clousure - Nova | 20 - Closing Zones - Nova | 21 - Recuperation - Nova | 22 - Nova Bus Finishing Area - Nova | 23 - Nova Bus Coach Tester Inspection - Nova | 24 - Nova Bus Coach Tester Road Test, Inspection & Painting | 25 - Nova Bus Coach Tester Water Test, Repairs after Road Test | 26 - Cleaning & Washing Before Presenting | 27 - Customer Validation - Nova | 28 - Repairs after Customer Inspection - Nova | 29 - Customer Pre-Delivery Sign Off - Nova
LF76-01 | 2NVYL82M5S3754808 | 76001 | Remi | 2/7/2025 | 2/10/2025 | 2/10/2025 | 2/10/2025 | 2/11/2025 | 2/11/2025 | 2/11/2025 | 2/12/2025 | 2/12/2025 | 2/12/2025 | 2/13/2025 | 2/13/2025 | 2/14/2025 | 2/14/2025 | 2/14/2025 | 2/17/2025 | 2/17/2025 | 2/18/2025 | 2/18/2025 | 2/19/2025 | 2/19/2025 | 2/20/2025
LF76-01 | 2NVYL82M5S3754808 | 76001 | Stephane
LF76-02 | 2NVYL82M7S3754874 | 76002 | Remi | 3/20/2025 | 3/20/2025 | 3/20/2025 | 3/21/2025 | 3/21/2025 | 3/24/2025 | 3/24/2025 | 3/25/2025 | 3/25/2025 | 3/26/2025 | 3/26/2025 | 3/27/2025 | 3/27/2025 | 3/27/2025 | 3/28/2025 | 3/28/2025 | 3/28/2025 | 3/31/2025 | 3/31/2025 | 3/31/2025 | 4/1/2025 | 4/1/2025 | 4/1/2025
LF76-02 | 2NVYL82M7S3754874 | 76002 | Stephane
LF76-03 | 2NVYL82M9S3754875 | 76003 | Remi | 3/20/2025 | 3/20/2025 | 3/21/2025 | 3/21/2025 | 3/24/2025 | 3/24/2025 | 3/25/2025 | 3/25/2025 | 3/25/2025 | 3/26/2025 | 3/26/2025 | 3/27/2025 | 3/27/2025 | 3/27/2025 | 3/28/2025 | 3/28/2025 | 3/31/2025 | 3/31/2025 | 3/31/2025 | 4/1/2025 | 4/1/2025 | 4/1/2025
LF76-03 | 2NVYL82M9S3754875 | 76003 | Stephane
LF76-04 | 2NVYL82M0S3754876 | 76004 | Remi | 3/20/2025 | 3/21/2025 | 3/21/2025 | 3/24/2025 | 3/25/2025 | 3/25/2025 | 3/25/2025 | 3/26/2025 | 3/26/2025 | 3/26/2025 | 3/27/2025 | 3/27/2025 | 3/27/2025 | 3/28/2025 | 3/28/2025 | 3/31/2025 | 3/31/2025 | 4/1/2025 |  | 4/1/2025
LF76-04 | 2NVYL82M0S3754876 | 76004 | Stephane
LF76-05 | 2NVYL82M2S3754877 | 76005 | Remi | 3/21/2025 | 3/21/2025 | 3/24/2025 | 3/24/2025 | 3/25/2025 | 3/25/2025 | 3/25/2025 | 3/26/2025 | 3/27/2025 | 3/27/2025 | 3/27/2025 | 3/28/2025 | 3/28/2025 | 3/28/2025 | 3/31/2025 | 3/31/2025 | 4/1/2025 | 4/1/2025
LF76-05 | 2NVYL82M2S3754877 | 76005 | Stephane
DEMO-03312005 | NO VIN | DEMO-03312005 | Remi Test
LF76-06 | 2NVYL82M6S3754896 | 76006 | Gaetan 2 | [5 empty] | 4/4/2025 | 4/4/2025
LF76-06 | 2NVYL82M6S3754896 | 76006 | Remi | 4/3/2025 | 4/3/2025 | 4/4/2025 | 4/4/2025 | 4/7/2025 | 4/7/2025 | 4/7/2025 | 4/8/2025 | 4/8/2025 | 4/8/2025 | 4/9/2025 | 4/9/2025 | 4/9/2025 | 4/10/2025 | 4/10/2025 | 4/10/2025
LF76-06 | 2NVYL82M6S3754896 | 76006 | Stephane
LF76-07 | 2NVYL82M8S3754897 | 76007 | Gaetan 2 |  |  |  |  | 4/4/2025 | 4/4/2025
LF76-07 | 2NVYL82M8S3754897 | 76007 | Remi | 4/4/2025 | 4/4/2025 | 4/4/2025 | 4/7/2025 | 4/7/2025 | 4/7/2025 | 4/8/2025 | 4/8/2025 | 4/8/2025 | 4/9/2025 | 4/9/2025 | 4/9/2025 | 4/10/2025 | 4/10/2025 | 4/10/2025 | 4/11/2025 | 4/14/2025 | 4/14/2025 | 4/2/2025
LF76-07 | 2NVYL82M8S3754897 | 76007 | Stephane
LF76-08 | 2NVYL82MXS3754898 | 76008 | Gaetan 2 |  |  |  | 4/4/2025 | 4/4/2025
LF76-08 | 2NVYL82MXS3754898 | 76008 | Remi | 4/4/2025 | 4/4/2025 | 4/7/2025 | 4/7/2025 | 4/7/2025 | 4/8/2025 | 4/8/2025 | 4/8/2025 | 4/9/2025 | 4/9/2025 | 4/9/2025 | 4/10/2025 | 4/10/2025 | 4/10/2025 | 4/11/2025 | 4/11/2025 | 4/14/2025 | 4/14/2025 | 4/14/2025
LF76-08 | 2NVYL82MXS3754898 | 76008 | Stephane
LF76-09 | 2NVYL82M1S3754899 | 76009 | Gaetan 2 |  |  | 4/4/2025 | 4/4/2025
LF76-09 | 2NVYL82M1S3754899 | 76009 | Remi | 4/4/2025 | 4/4/2025 | 4/7/2025 | 4/7/2025 | 4/7/2025 | 4/8/2025 | 4/8/2025 | 4/8/2025 | 4/9/2025 | 4/9/2025 | 4/9/2025 | 4/10/2025 | 4/10/2025 | 4/11/2025 | 4/11/2025 | 4/11/2025 | 4/14/2025 | 4/14/2025 | 4/14/2025
LF76-09 | 2NVYL82M1S3754899 | 76009 | Stephane
LF76-10 | 2NVYL82M4S3754900 | 76010 | Gaetan 2 |  | 4/4/2025 | 4/4/2025
LF76-10 | 2NVYL82M4S3754900 | 76010 | Remi | 4/7/2025 | 4/7/2025 | 4/7/2025 | 4/8/2025 | 4/8/2025 | 4/8/2025 | 4/9/2025 | 4/9/2025 | 4/9/2025 | 4/10/2025 | 4/10/2025 | 4/10/2025 | 4/11/2025 | 4/11/2025 | 4/14/2025 | 4/14/2025 | 4/14/2025
LF76-10 | 2NVYL82M4S3754900 | 76010 | Stephane
LF76-11 | 2NVYL82M6S3754901 | LF76-11 | Gaetan 2
LF76-11 | 2NVYL82M6S3754901 | LF76-11 | Remi | 4/6/2025 | 4/7/2025 | 4/8/2025 | 4/8/2025 | 4/8/2025 | 4/9/2025 | 4/9/2025 | 4/9/2025 | 4/10/2025 | 4/10/2025 | 4/10/2025 | 4/11/2025 | 4/11/2025 | 4/11/2025 | 4/14/2025 | 4/14/2025 | 4/14/2025
LF76-12 | 2NVYL82M8S3754902 | LF76-12 | Gaetan 2
LF76-12 | 2NVYL82M8S3754902 | LF76-12 | Remi | 4/6/2025 | 4/7/2025 | 4/7/2025 | 4/8/2025 | 4/8/2025 | 4/9/2025 | 4/9/2025 | 4/10/2025 | 4/10/2025 | 4/10/2025 | 4/11/2025 | 4/11/2025 | 4/11/2025 | 4/14/2025 | 4/14/2025 | 4/14/2025
LF76-13 | 2NVYL82MXS3754903 | LF76-13 | Gaetan 2
LF76-13 | 2NVYL82MXS3754903 | LF76-13 | Remi | 4/6/2025 | 4/7/2025 | 4/8/2025 | 4/8/2025 | 4/9/2025 | 4/9/2025 | 4/9/2025 | 4/10/2025 | 4/10/2025 | 4/11/2025 | 4/11/2025 | 4/11/2025 | 4/14/2025 | 4/14/2025 | 4/14/2025
LF76-14 | 2NVYL82M1S3754904 | LF76-14 | Gaetan 2
LF76-14 | 2NVYL82M1S3754904 | LF76-14 | Remi | 4/6/2025 | 4/7/2025 | 4/8/2025 | 4/9/2025 | 4/9/2025 | 4/9/2025 | 4/10/2025 | 4/10/2025 | 4/10/2025 | 4/10/2025 | 4/11/2025 | 4/11/2025 | 4/14/2025 | 4/14/2025 | 4/14/2025
LF76-14 | 2NVYL82M1S3754904 | LF76-14 | Stephane
LF76-15 | 2NVYL82MXS3754920 | 76015 | Remi | 4/16/2025 | 4/16/2025 | 4/30/2025 | 4/30/2025 | 4/30/2025 | 4/30/2025 | 4/30/2025 | 4/30/2025 | 4/30/2025 | 4/30/2025 | 4/30/2025 | 4/30/2025 | 4/30/2025 | 4/30/2025 | 4/30/2025 | 4/30/2025 | 4/30/2025 | 4/30/2025 |  | 4/30/2025 | 4/30/2025
LF76-15 | 2NVYL82MXS3754920 | 76015 | Stephane
LF76-16 | 2NVYL82M1S3754921 | 76016 | Remi | 4/2/2025 | 4/2/2025 | 4/2/2025 | 4/2/2025 | 4/2/2025 | 4/2/2025 | 4/2/2025 | 4/2/2025 | 4/2/2025 | 4/2/2025 | 4/2/2025 | 4/2/2025 | 4/2/2025 | 4/2/2025 | 4/2/2025 | 4/2/2025 | 4/2/2025 | 4/2/2025 | 4/2/2025 | 4/2/2025
LF76-17 | 2NVYL82M1S3754922 | 76017 | Remi
LF76-18 | 2NVYL82M1S3754923 | 76018 | Remi
LF76-18 | 2NVYL82M1S3754923 | 76018 | Stephane
LF76-18 | 2NVYL82M1S3754923 | 76018 | Gaetan 2
LF76-19 | 2NVYL82M1S3754924 | 76019 | Remi
LF76-20 | 2NVYL82M1S3754925 | 76020 | Remi
LF76-20 | 2NVYL82M1S3754925 | 76020 | Stephane
LF76-21 | 2NVYL82M1S3754935 | 76021 | Remi | 4/25/2025 | 4/28/2025 | 4/28/2025 | 4/28/2025 | 4/29/2025 | 4/29/2025 | 4/29/2025 | 4/30/2025 | 4/30/2025 | 4/30/2025 | 5/1/2025 | 5/1/2025 | 5/1/2025 | 5/2/2025 | 5/2/2025 | 5/5/2025 | 5/5/2025 | 5/5/2025 | 5/6/2025 | 5/6/2025 | 5/6/2025 | 5/7/2025
LF76-21 | 2NVYL82M1S3754935 | 76021 | Stephane
LF76-22 | 2NVYL82M3S3754936 | 76022 | Remi | 4/28/2025 | 4/28/2025 | 4/28/2025 | 4/29/2025 | 4/29/2025 | 4/29/2025 | 4/30/2025 | 4/30/2025 | 4/30/2025 | 5/1/2025 | 5/1/2025 | 5/1/2025 | 5/2/2025 | 5/2/2025 | 5/5/2025 | 5/5/2025 | 5/5/2025 | 5/6/2025 | 5/7/2025 | 5/6/2025 | 5/6/2025 | 5/7/2025
LF76-22 | 2NVYL82M3S3754936 | 76022 | Gaetan 2
LF76-22 | 2NVYL82M3S3754936 | 76022 | Stephane
LF76-23 | 2NVYL82M5S3754937 | 76023 | Remi | 4/28/2025 | 4/28/2025 | 4/29/2025 | 4/29/2025 | 4/29/2025 | 4/30/2025 | 4/30/2025 | 4/30/2025 | 5/1/2025 | 5/1/2025 | 5/1/2025 | 5/2/2025 | 5/2/2025 | 5/5/2025 | 5/5/2025 | 5/5/2025 | 5/6/2025 | 5/6/2025 | 5/6/2025 | 5/6/2025 | 5/7/2025
LF76-24 | 2NVYL82M7S3754938 | 76024 | Remi | 4/28/2025 | 4/29/2025 | 4/29/2025 | 4/29/2025 | 4/30/2025 | 4/30/2025 | 4/30/2025 | 5/1/2025 | 5/1/2025 | 5/1/2025 | 5/2/2025 | 5/2/2025 | 5/5/2025 | 5/5/2025 | 5/5/2025 | 5/6/2025 | 5/6/2025 | 5/6/2025 | 5/6/2025 | 5/7/2025 | 5/8/2025
LF76-25 | 2NVYL82M9S3754939 | 76025 | Remi | 4/29/2025 | 4/29/2025 | 4/29/2025 | 4/30/2025 | 4/30/2025 | 4/30/2025 | 5/1/2025 | 5/1/2025 | 5/1/2025 | 5/2/2025 | 5/2/2025 | 5/5/2025 | 5/5/2025 | 5/5/2025 | 5/6/2025 | 5/6/2025 | 5/6/2025 | 5/7/2025 | 5/7/2025 | 5/8/2025 | 5/8/2025
LF76-25 | 2NVYL82M9S3754939 | 76025 | Stephane
LF76-26 | 2NVYL82M5S3754954 | 76026 | Remi | 5/6/2025 | 5/7/2025 | 5/7/2025 | 5/8/2025 | 5/8/2025 | 5/8/2025 | 5/9/2025 | 5/12/2025 | 5/12/2025 | 5/12/2025 | 5/13/2025 | 5/13/2025 | 5/13/2025 | 5/14/2025 | 5/14/2025 | 5/14/2025 | 5/15/2025 | 5/15/2025 | 5/15/2025 | 5/16/2025
LF76-26 | 2NVYL82M5S3754954 | 76026 | Stephane
LF76-26 | 2NVYL82M5S3754954 | 76026 | Gaetan 2
LF76-27 | 2NVYL82M7S3754955 | 76027 | Remi | 5/7/2025 | 5/7/2025 | 5/8/2025 | 5/8/2025 | 5/8/2025 | 5/9/2025 | 5/12/2025 | 5/12/2025 | 5/12/2025 | 5/13/2025 | 5/13/2025 | 5/13/2025 | 5/14/2025 | 5/14/2025 | 5/14/2025 | 5/15/2025 | 5/15/2025 | 5/15/2025 | 5/16/2025 | 5/16/2025
LF76-27 | 2NVYL82M7S3754955 | 76027 | Gaetan 2
LF76-27 | 2NVYL82M7S3754955 | 76027 | Stephane
LF76-28 | 2NVYL82M9S3754956 | 76028 | Remi | 5/7/2025 | 5/8/2025 | 5/8/2025 | 5/8/2025 | 5/9/2025 | 5/12/2025 | 5/12/2025 | 5/12/2025 | 5/13/2025 | 5/13/2025 | 5/13/2025 | 5/14/2025 | 5/14/2025 | 5/14/2025 | 5/15/2025 | 5/15/2025 | 5/15/2025 | 5/16/2025 | 5/16/2025 | 5/16/2025
LF76-28 | 2NVYL82M9S3754956 | 76028 | Stephane
LF76-29 | 2NVYL82M0S3754957 | 76029 | Remi | 5/8/2025 | 5/8/2025 | 5/8/2025 | 5/9/2025 | 5/12/2025 | 5/12/2025 | 5/12/2025 | 5/13/2025 | 5/13/2025 | 5/13/2025 | 5/14/2025 | 5/14/2025 | 5/14/2025 | 5/15/2025 | 5/15/2025 | 5/15/2025 | 5/16/2025 | 5/16/2025 | 5/16/2025 | 5/19/2025
LF76-29 | 2NVYL82M0S3754957 | 76029 | Stephane
LF76-30 | NO VIN | LF76-30 | Remi | 5/21/2025 | 5/22/2025 | 5/22/2025 | 5/23/2025 | 5/23/2025 | 5/26/2025 | 5/26/2025 | 5/26/2025 | 5/27/2025 | 5/27/2025 | 5/28/2025 | 5/27/2025 | 5/29/2025 | 5/29/2025 | 5/28/2025 | 5/30/2025 | 5/29/2025 | 6/2/2025 | 6/3/2025 | 6/3/2025
LF76-30 | NO VIN | LF76-30 | Stephane
LF76-31 | NO VIN | LF76-31 | Remi | 5/22/2025 | 5/22/2025 | 5/23/2025 | 5/23/2025 | 5/26/2025 | 5/26/2025 | 5/26/2025 | 5/27/2025 | 5/27/2025 | 5/28/2025 | 5/28/2025 | 5/29/2025 | 5/29/2025 | 5/28/2025 | 5/30/2025 | 5/29/2025 | 6/2/2025 | 6/3/2025 | 6/3/2025 | 6/3/2025
LF76-31 | NO VIN | LF76-31 | Stephane
LF76-32 | NO VIN | LF76-32 | Remi | 5/22/2025 | 5/23/2025 | 5/23/2025 | 5/26/2025 | 5/26/2025 | 5/26/2025 | 5/27/2025 | 5/27/2025 | 5/28/2025 | 5/28/2025 | 5/29/2025 | 5/29/2025 | 5/30/2025 | 5/30/2025 | 5/29/2025 | 6/2/2025 | 6/3/2025 | 6/3/2025 | 6/3/2025 | 9/9/2025 | 9/9/2025 | 9/9/2025 | 9/9/2025 | 9/9/2025 | 9/9/2025 | 9/9/2025 | 9/9/2025 | 9/9/2025
LF76-32 | NO VIN | LF76-32 | Stephane
LF76-33 | NO VIN | LF76-33 | Remi | 5/23/2025 | 5/23/2025 | 5/26/2025 | 5/26/2025 | 5/26/2025 | 5/27/2025 | 5/27/2025 | 5/28/2025 | 5/28/2025 | 5/29/2025 | 5/29/2025 | 5/30/2025 | 5/30/2025 | 5/29/2025 | 5/29/2025 | 6/3/2025 | 6/3/2025 | 6/3/2025 | 6/4/2025
LF76-33 | NO VIN | LF76-33 | Gaetan 2
LF76-33 | NO VIN | LF76-33 | Stephane
LF76-34 | 2NVYL82M2S3755009 | 76034 | Daniel2 | 6/6/2025 | 6/9/2025 | 6/9/2025 | 6/10/2025 | 6/10/2025 | 6/11/2025 | 6/11/2025 | 6/12/2025 | 6/12/2025 | 6/12/2025 | 6/13/2025 | 6/13/2025 | 6/16/2025 | 6/16/2025 | 6/17/2025 | 6/17/2025 | 6/17/2025 | 6/18/2025 |  | 6/18/2025 | 6/18/2025 | 6/6/2025 | 6/9/2025 | 6/9/2025 | 6/10/2025 | 6/10/2025 |  |  | 6/18/2025
LF76-34 | 2NVYL82M2S3755009 | 76034 | Remi
LF76-34 | 2NVYL82M2S3755009 | 76034 | Stephane
LF76-35 | 2NVYL82M9S3755010 | 76035 | Daniel2 |  |  |  |  | 6/11/2025 | 6/11/2025 | 6/12/2025 | 6/12/2025 | 6/12/2025 | 6/13/2025 | 6/13/2025 | 6/13/2025 | 6/16/2025 | 6/16/2025 | 6/17/2025 | 6/17/2025 | 6/17/2025 | 6/18/2025 |  | 6/18/2025 | 6/18/2025
LF76-35 | 2NVYL82M9S3755010 | 76035 | Remi
LF76-35 | 2NVYL82M9S3755010 | 76035 | Stephane
LF76-35 | 2NVYL82M9S3755010 | 76035 | Gaetan 2
LF76-36 | 2NVYL82M0S3755011 | 76036 | Daniel2 |  |  |  | 6/11/2025 | 6/11/2025 | 6/12/2025 | 6/12/2025 | 6/12/2025 | 6/12/2025 | 6/12/2025 | 6/12/2025 | 6/13/2025 | 6/13/2025 | 6/16/2025 | 6/16/2025 | 6/17/2025 | 6/17/2025 | 6/18/2025 |  | 6/18/2025 | 6/18/2025
LF76-36 | 2NVYL82M0S3755011 | 76036 | Remi
LF76-36 | 2NVYL82M0S3755011 | 76036 | Stephane
LF76-36 | 2NVYL82M0S3755011 | 76036 | Gaetan 2
LF76-37 | 2NVYL82M2S3755012 | 76037 | Daniel2 |  |  | 6/11/2025 | 6/11/2025 | 6/12/2025 | 6/12/2025 | 6/12/2025 | 6/13/2025 | 6/13/2025 | 6/13/2025 | 6/13/2025 | 6/16/2025 | 6/16/2025 | 6/16/2025 | 6/17/2025 | 6/17/2025 | 6/17/2025 | 6/18/2025 |  | 6/18/2025 | 6/19/2025 | [7 empty] | 6/19/2025
LF76-37 | 2NVYL82M2S3755012 | 76037 | Remi
LF76-37 | 2NVYL82M2S3755012 | 76037 | Stephane
LF76-38 | 2NVYL82M3S3755035 | LF76-38 | Gaetan 2 | [13 empty] | 7/1/2025 | 7/1/2025 | 7/2/2025 | 7/2/2025 | 7/2/2025
LF76-38 | 2NVYL82M3S3755035 | LF76-38 | Remi | [19 empty] | 7/3/2025 | 7/3/2025
LF76-38 | 2NVYL82M3S3755035 | LF76-38 | Stephane
LF76-39 | 2NVYL82M5S3755036 | LF76-39 | Gaetan 2 | [12 empty] | 7/1/2025 | 7/1/2025 | 7/2/2025 | 7/2/2025 | 7/2/2025
LF76-39 | 2NVYL82M5S3755036 | LF76-39 | Remi | [19 empty] | 7/3/2025 | 7/3/2025
LF76-39 | 2NVYL82M5S3755036 | LF76-39 | Stephane
LF76-40 | 2NVYL82M7S3755037 | LF76-40 | Gaetan 2 | [11 empty] | 7/1/2025 | 7/1/2025 | 7/2/2025 | 7/2/2025 | 7/2/2025
LF76-40 | 2NVYL82M7S3755037 | LF76-40 | Remi | [17 empty] | 7/3/2025 |  | 7/3/2025 | 7/3/2025
LF76-40 | 2NVYL82M7S3755037 | LF76-40 | Stephane
LF76-41 | 2NVYL82M9S3755038 | LF76-41 | Gaetan 2 | [10 empty] | 7/1/2025 | 7/1/2025 | 7/2/2025 | 7/2/2025 | 7/2/2025
LF76-41 | 2NVYL82M9S3755038 | LF76-41 | Remi | [16 empty] | 7/3/2025 | 7/3/2025 |  | 7/3/2025 | 7/4/2025
LF76-41 | 2NVYL82M9S3755038 | LF76-41 | Stephane
LF76-42 | 2NVYL82M0S3755039 | LF76-42 | Gaetan 2 | [9 empty] | 7/1/2025 | 7/1/2025 | 7/2/2025 | 7/2/2025 | 7/2/2025
LF76-42 | 2NVYL82M0S3755039 | LF76-42 | Remi | [15 empty] | 7/3/2025 | 7/3/2025 | 7/3/2025 |  | 7/4/2025 | 7/4/2025
LF76-42 | 2NVYL82M0S3755039 | LF76-42 | Stephane
LF76-43 | 2NVYL82M7S3755040 | LF76-43 | Gaetan 2 | [8 empty] | 7/2/2025 | 7/2/2025 | 7/2/2025
LF76-43 | 2NVYL82M7S3755040 | LF76-43 | Remi | [11 empty] | 7/3/2025 | 7/3/2025 | 7/3/2025 | 7/4/2025 | 7/4/2025 | 7/7/2025 | 7/7/2025 |  | 7/7/2025 | 7/8/2025
LF76-43 | 2NVYL82M7S3755040 | LF76-43 | Stephane
LF76-43 | 2NVYL82M7S3755040 | LF76-43 | Richard L
LF76-44 | 2NVYL82M9S3755041 | LF76-44 | Remi | [10 empty] | 7/3/2025 | 7/3/2025 | 7/3/2025 | 7/4/2025 | 7/4/2025 | 7/7/2025 | 7/7/2025 | 7/7/2025 |  | 7/8/2025 | 7/8/2025
LF76-44 | 2NVYL82M9S3755041 | LF76-44 | Gaetan 2 | [7 empty] | 7/2/2025 | 7/2/2025 | 7/2/2025
LF76-44 | 2NVYL82M9S3755041 | LF76-44 | Stephane
LF76-45 | 2NVYL82M0S3755042 | LF76-45 | Remi | [9 empty] | 7/3/2025 | 7/3/2025 | 7/3/2025 | 7/4/2025 | 7/4/2025 | 7/7/2025 | 7/7/2025 | 7/7/2025 | 7/8/2025 |  | 7/8/2025 | 7/8/2025
LF76-45 | 2NVYL82M0S3755042 | LF76-45 | Gaetan 2 | [6 empty] | 7/2/2025 | 7/2/2025 | 7/2/2025
LF76-45 | 2NVYL82M0S3755042 | LF76-45 | Stephane
LF76-46 | 2NVYL82M2S3755043 | LF76-46 | Remi | [8 empty] | 7/3/2025 | 7/3/2025 | 7/3/2025 | 7/4/2025 | 7/4/2025 | 7/7/2025 | 7/7/2025 | 7/7/2025 | 7/8/2025 | 7/8/2025 |  | 7/8/2025
LF76-46 | 2NVYL82M2S3755043 | LF76-46 | Gaetan 2 | [5 empty] | 7/2/2025 | 7/2/2025 | 7/2/2025
LF76-46 | 2NVYL82M2S3755043 | LF76-46 | Stephane
LF76-47 | 2NVYL82M4S3755044 | LF76-47 | Remi | [7 empty] | 7/3/2025 | 7/3/2025 | 7/3/2025 | 7/4/2025 | 7/4/2025 | 7/7/2025 | 7/7/2025 | 7/7/2025 | 7/8/2025 | 7/8/2025 | 7/8/2025 |  | 7/8/2025
LF76-47 | 2NVYL82M4S3755044 | LF76-47 | Gaetan 2 |  |  |  |  | 7/2/2025 | 7/2/2025 | 7/2/2025
LF76-47 | 2NVYL82M4S3755044 | LF76-47 | Stephane
LF76-48 | 2NVYL82M8S3755077 | LF76-48 | Remi
LF76-48 | 2NVYL82M8S3755077 | LF76-48 | Stephane
LF76-48 | 2NVYL82M8S3755077 | LF76-48 | Gaetan 2 | [17 empty] | 7/17/2025
LF76-49 | 2NVYL82MXS3755078 | LF76-49 | Stephane
LF76-49 | 2NVYL82MXS3755078 | LF76-49 | Gaetan 2 | [17 empty] | 7/17/2025
LF76-49 | 2NVYL82MXS3755078 | LF76-49 | Remi
LF76-50 | 2NVYL82M1S3755079 | LF76-50 | Gaetan 2 | [16 empty] | 7/17/2025 | 7/18/2025
LF76-50 | 2NVYL82M1S3755079 | LF76-50 | Remi
LF76-50 | 2NVYL82M1S3755079 | LF76-50 | Stephane
LF76-51 | 2NVYL82M8S3755080 | LF76-51 | Gaetan 2 | [15 empty] | 7/17/2025 | 7/17/2025 | 7/18/2025
LF76-51 | 2NVYL82M8S3755080 | LF76-51 | Remi
LF76-51 | 2NVYL82M8S3755080 | LF76-51 | Stephane
LF76-51 | 2NVYL82M8S3755080 | LF76-51 | Richard L
LF76-52 | 2NVYL82MXS3755081 | LF76-52 | Gaetan 2 | [13 empty] | 7/17/2025 | 7/17/2025 | 7/18/2025 | 7/18/2025 | 7/18/2025
LF76-52 | 2NVYL82MXS3755081 | LF76-52 | Remi
LF76-52 | 2NVYL82MXS3755081 | LF76-52 | Stephane
LF76-53 | 2NVYL82M1S3755082 | LF76-53 | Gaetan 2 | [16 empty] | 7/18/2025 | 7/18/2025
LF76-53 | 2NVYL82M1S3755082 | LF76-53 | Remi
LF76-53 | 2NVYL82M1S3755082 | LF76-53 | Stephane
LF76-54 | 2NVYL82M3S3755083 | LF76-54 | Gaetan 2 | [11 empty] | 7/17/2025 | 7/17/2025 | 7/18/2025 | 7/18/2025 | 7/18/2025 | 7/18/2025
LF76-54 | 2NVYL82M3S3755083 | LF76-54 | Remi
LF76-54 | 2NVYL82M3S3755083 | LF76-54 | Stephane
LF76-55 | 2NVYL82M5S3755084 | LF76-55 | Gaetan 2 | [10 empty] | 7/17/2025 | 7/17/2025 | 7/18/2025 | 7/18/2025 | 7/18/2025 | 7/18/2025 | 7/18/2025 | 8/11/2025
LF76-55 | 2NVYL82M5S3755084 | LF76-55 | Remi
LF76-55 | 2NVYL82M5S3755084 | LF76-55 | Stephane
LF76-56 | 2NVYL82M7S3755085 | LF76-56 | Gaetan 2 | [9 empty] | 7/17/2025 | 7/17/2025 | 7/18/2025 | 7/18/2025 | 7/18/2025 | 7/18/2025 |  | 8/11/2025 | 8/12/2025
LF76-56 | 2NVYL82M7S3755085 | LF76-56 | Remi
LF76-56 | 2NVYL82M7S3755085 | LF76-56 | Richard L
LF76-56 | 2NVYL82M7S3755085 | LF76-56 | Stephane
LF76-57 | 2NVYL82M9S3755086 | LF76-57 | Gaetan 2 | [8 empty] | 7/17/2025 | 7/17/2025 | 7/18/2025 | 7/18/2025 | 7/18/2025 |  |  | 8/11/2025 |  | 8/12/2025
LF76-57 | 2NVYL82M9S3755086 | LF76-57 | Remi
LF76-57 | 2NVYL82M9S3755086 | LF76-57 | Stephane
LF76-58 | 2NVYL82M0S3755087 | LF76-58 | Gaetan 2 | [7 empty] | 7/17/2025 | 7/17/2025 | 7/18/2025 | 7/18/2025 | 7/18/2025 |  |  | 8/11/2025 |  |  | 8/12/2025
LF76-58 | 2NVYL82M0S3755087 | LF76-58 | Richard L
LF76-58 | 2NVYL82M0S3755087 | LF76-58 | Stephane
LF76-58 | 2NVYL82M0S3755087 | LF76-58 | Remi
LF76-59 | 2NVYL82M2S3755088 | LF76-59 | Gaetan 2 | [6 empty] | 7/17/2025 | 7/17/2025 | 7/18/2025 | 7/18/2025 | 7/18/2025 | 7/18/2025 | 7/18/2025 | 8/11/2025 |  |  | 8/12/2025 | 8/12/2025
LF76-59 | 2NVYL82M2S3755088 | LF76-59 | Remi
LF76-59 | 2NVYL82M2S3755088 | LF76-59 | Stephane
LF76-59 | 2NVYL82M2S3755088 | LF76-59 | Richard L
LF76-60 | 2NVYL82MXS3755095 | LF76-60 | Gaetan 2 | [11 empty] | 8/15/2025 | 8/15/2025 | 8/15/2025 | 8/18/2025 | 8/18/2025 | 8/19/2025 | 8/19/2025
LF76-60 | 2NVYL82MXS3755095 | LF76-60 | Remi
LF76-60 | 2NVYL82MXS3755095 | LF76-60 | Stephane
LF76-61 | 2NVYL82M1S3755096 | LF76-61 | Gaetan 2 | [10 empty] | 8/15/2025 | 8/15/2025 | 8/15/2025 | 8/18/2025 | 8/19/2025 | 8/19/2025 | 8/19/2025 | 8/19/2025
LF76-61 | 2NVYL82M1S3755096 | LF76-61 | Remi
LF76-61 | 2NVYL82M1S3755096 | LF76-61 | Stephane
LF76-62 | 2NVYL82M3S3755097 | LF76-62 | Gaetan 2 | [9 empty] | 8/15/2025 | 8/15/2025 | 8/15/2025 | 8/18/2025 | 8/18/2025 | 8/19/2025 | 8/19/2025 | 8/19/2025 | 8/19/2025
LF76-62 | 2NVYL82M3S3755097 | LF76-62 | Remi
LF76-62 | 2NVYL82M3S3755097 | LF76-62 | Stephane
LF76-62 | 2NVYL82M3S3755097 | LF76-62 | Richard L
LF76-63 | 2NVYL82M5S3755098 | LF76-63 | Gaetan 2 | [8 empty] | 8/15/2025 | 8/15/2025 | 8/15/2025 | 8/18/2025 | 8/18/2025 | 8/19/2025 | 8/19/2025 | 8/19/2025 | 8/19/2025 | 8/19/2025
LF76-63 | 2NVYL82M5S3755098 | LF76-63 | Remi
LF76-63 | 2NVYL82M5S3755098 | LF76-63 | Stephane
LF76-64 | 2NVYL82M7S3755099 | LF76-64 | Gaetan 2 | [12 empty] | 8/19/2025 | 8/19/2025 | 8/19/2025 | 8/20/2025 | 8/20/2025 | 8/20/2025
LF76-64 | 2NVYL82M7S3755099 | LF76-64 | Remi
LF76-64 | 2NVYL82M7S3755099 | LF76-64 | Stephane
LF76-64 | 2NVYL82M7S3755099 | LF76-64 | Richard L
LF76-65 | 2NVYL82MXS3755100 | LF76-65 | Gaetan 2 | [11 empty] | 8/19/2025 | 8/19/2025 | 8/19/2025 | 8/20/2025 | 8/20/2025 | 8/20/2025 | 8/21/2025
LF76-65 | 2NVYL82MXS3755100 | LF76-65 | Remi
LF76-65 | 2NVYL82MXS3755100 | LF76-65 | Richard L
LF76-65 | 2NVYL82MXS3755100 | LF76-65 | Stephane
LF76-66 | 2NVYL82M1S3755101 | LF76-66 | Gaetan 2 | [8 empty] | 8/19/2025 | 8/19/2025 | 8/19/2025 | 8/20/2025 | 8/20/2025 | 8/20/2025 | 8/21/2025 | 8/21/2025 | 8/21/2025 | 8/22/2025
LF76-66 | 2NVYL82M1S3755101 | LF76-66 | Remi
LF76-66 | 2NVYL82M1S3755101 | LF76-66 | Stephane
LF76-67 | 2NVYL82M3S3755102 | LF76-67 | Gaetan 2 | [7 empty] | 8/19/2025 | 8/19/2025 | 8/19/2025 | 8/20/2025 | 8/20/2025 | 8/20/2025 | 8/21/2025 | 8/21/2025 | 8/21/2025 | 8/22/2025 | 8/25/2025
LF76-67 | 2NVYL82M3S3755102 | LF76-67 | Remi
LF76-67 | 2NVYL82M3S3755102 | LF76-67 | Stephane
LF76-68 | 2NVYL82M5S3755103 | LF76-68 | Gaetan 2 |  |  |  | 8/19/2025 | 8/19/2025 | 8/19/2025 | 8/20/2025 | 8/20/2025 | 8/20/2025 | 8/20/2025 | 8/20/2025 | 8/20/2025 | 8/21/2025 | 8/21/2025 | 8/21/2025 | 8/22/2025 | 8/22/2025 | 8/22/2025
LF76-68 | 2NVYL82M5S3755103 | LF76-68 | Remi
LF76-68 | 2NVYL82M5S3755103 | LF76-68 | Stephane
LF76-68 | 2NVYL82M5S3755103 | LF76-68 | Richard L
LF76-69 | 2NVYL82M7S3755104 | LF76-69 | Gaetan 2 | [5 empty] | 8/19/2025 | 8/19/2025 | 8/19/2025 | 8/20/2025 | 8/20/2025 | 8/20/2025 | 8/21/2025 | 8/21/2025 | 8/21/2025 | 8/21/2025 | 8/22/2025 | 8/22/2025 | 8/25/2025
LF76-69 | 2NVYL82M7S3755104 | LF76-69 | Remi
LF76-69 | 2NVYL82M7S3755104 | LF76-69 | Stephane
LF76-69 | 2NVYL82M7S3755104 | LF76-69 | Richard L
LF76-70 | 2NVYL82M9S3755105 | LF76-70 | Gaetan 2 | [7 empty] | 8/20/2025 | 8/20/2025 | 8/20/2025 | 8/21/2025 | 8/21/2025 | 8/21/2025 | 8/21/2025 | 8/22/2025 | 8/22/2025 | 8/22/2025 | 8/25/2025
LF76-70 | 2NVYL82M9S3755105 | LF76-70 | Daniel2
LF76-70 | 2NVYL82M9S3755105 | LF76-70 | Remi
LF76-70 | 2NVYL82M9S3755105 | LF76-70 | Richard L
LF76-70 | 2NVYL82M9S3755105 | LF76-70 | Stephane
LF76-71 | 2NVYL82M8S3755113 | 76071 | Daniel
LF76-71 | 2NVYL82M8S3755113 | 76071 | Gaetan 2
LF76-71 | 2NVYL82M8S3755113 | 76071 | Daniel2 | 8/22/2025 | 8/22/2025 | 8/23/2025 | 8/23/2025 | 8/24/2025 | 8/25/2025 | 8/25/2025 | 8/25/2025 | 8/26/2025 | 8/25/2025 | 8/27/2025 | 8/27/2025 | 8/28/2025 | 8/28/2025 | 8/28/2025 | 8/29/2025 | 8/29/2025 | 8/30/2025 | 8/22/2025 | 9/1/2025 | 9/2/2025 | 8/18/2025 | 8/19/2025 | 8/19/2025 | 8/20/2025 | 8/20/2025 | 8/21/2025 | 8/21/2025 | 8/30/2025
LF76-71 | 2NVYL82M8S3755113 | 76071 | Richard L
LF76-71 | 2NVYL82M8S3755113 | 76071 | Remi
LF76-71 | 2NVYL82M8S3755113 | 76071 | Stephane
LF76-72 | 2NVYL82MXS3755114 | 76072 | Daniel
LF76-72 | 2NVYL82MXS3755114 | 76072 | Gaetan 2
LF76-72 | 2NVYL82MXS3755114 | 76072 | Daniel2 | 8/22/2025 | 8/22/2025 | 8/23/2025 | 8/23/2025 | 8/24/2025 | 8/24/2025 | 8/25/2025 | 8/25/2025 | 8/26/2025 | 8/25/2025 | 8/27/2025 | 8/27/2025 | 8/28/2025 | 8/28/2025 | 8/28/2025 | 8/29/2025 | 8/29/2025 | 8/29/2025 | 8/22/2025 | 8/31/2025 | 8/31/2025 | 8/29/2025 | 8/19/2025 | 8/19/2025 | 8/20/2025 | 8/20/2025 | 8/21/2025 | 8/21/2025
LF76-72 | 2NVYL82MXS3755114 | 76072 | Remi
LF76-72 | 2NVYL82MXS3755114 | 76072 | Richard L
LF76-72 | 2NVYL82MXS3755114 | 76072 | Stephane
LF76-73 | 2NVYL82M1S3755115 | 76073 | Daniel
LF76-73 | 2NVYL82M1S3755115 | 76073 | Gaetan 2
LF76-73 | 2NVYL82M1S3755115 | 76073 | Daniel2 | 8/23/2025 | 8/23/2025 | 8/24/2025 | 8/24/2025 | 8/25/2025 | 8/25/2025 | 8/26/2025 | 8/26/2025 | 8/26/2025 | 8/27/2025 | 8/27/2025 | 8/28/2025 | 9/28/2025 | 8/28/2025 | 8/29/2025 | 8/29/2025 | 8/30/2025 | 8/30/2025 | 8/24/2025 | 9/1/2025 | 9/1/2025 | 8/30/2025 | 8/20/2025 | 8/20/2025 | 8/21/2025 | 8/21/2025 | 8/22/2025 | 8/23/2025
LF76-73 | 2NVYL82M1S3755115 | 76073 | Remi
LF76-73 | 2NVYL82M1S3755115 | 76073 | Richard L
LF76-74 | 2NVYL82M3S3755116 | 76074 | Daniel
LF76-74 | 2NVYL82M3S3755116 | 76074 | Gaetan 2
LF76-74 | 2NVYL82M3S3755116 | 76074 | Daniel2 | 8/24/2025 | 8/24/2025 | 8/25/2025 | 8/25/2025 | 8/26/2025 | 8/26/2025 | 8/27/2025 | 8/27/2025 | 8/27/2025 | 8/28/2025 | 8/28/2025 | 8/29/2025 | 8/29/2025 | 8/30/2025 | 8/30/2025 | 8/30/2025 | 8/31/2025 | 8/31/2025 | 8/24/2025 | 9/2/2025 | 9/2/2025 | 8/31/2025 | 8/21/2025 | 8/21/2025 | 8/22/2025 | 8/22/2025 | 8/23/2025 | 8/23/2025
LF76-74 | 2NVYL82M3S3755116 | 76074 | Doyle Backup
LF76-74 | 2NVYL82M3S3755116 | 76074 | Remi
LF76-74 | 2NVYL82M3S3755116 | 76074 | Stephane
LF76-74 | 2NVYL82M3S3755116 | 76074 | Richard L
LF76-75 | 2NVYL82M5S3755117 | 76075 | Daniel
LF76-75 | 2NVYL82M5S3755117 | 76075 | Gaetan 2
LF76-75 | 2NVYL82M5S3755117 | 76075 | Daniel2 | 8/24/2025 | 8/24/2025 | 8/25/2025 | 8/25/2025 | 8/26/2025 | 8/27/2025 | 8/27/2025 | 8/27/2025 | 8/28/2025 | 8/28/2025 | 9/29/2025 | 8/29/2025 | 8/29/2025 | 8/30/2025 | 8/30/2025 | 8/30/2025 | 8/31/2025 | 8/31/2025 | 8/23/2025 | 9/2/2025 | 9/2/2025 | 8/20/2025 | 8/20/2025 | 8/21/2025 | 8/21/2025 | 8/22/2025 | 8/22/2025 | 8/23/2025 | 8/31/2025
LF76-75 | 2NVYL82M5S3755117 | 76075 | Remi
LF76-75 | 2NVYL82M5S3755117 | 76075 | Richard L
LF76-75 | 2NVYL82M5S3755117 | 76075 | Stephane
LF76-76 | 2NVYL82M7S3755118 | 76076 | Daniel
LF76-76 | 2NVYL82M7S3755118 | 76076 | Gaetan 2
LF76-76 | 2NVYL82M7S3755118 | 76076 | Daniel2 | 8/24/2025 | 8/25/2025 | 8/25/2025 | 8/26/2025 | 8/26/2025 | 8/27/2025 | 8/27/2025 | 8/28/2025 | 8/28/2025 | 8/29/2025 | 9/1/2025 | 9/1/2025 | 8/31/2025 | 8/31/2025 | 8/31/2025 | 9/1/2025 | 9/1/2025 | 9/1/2025 | 8/25/2025 | 9/3/2025 | 9/3/2025 | 8/21/2025 | 8/21/2025 | 8/22/2025 | 8/23/2025 | 8/23/2025 | 8/24/2025 | 8/24/2025 | 9/2/2025
LF76-76 | 2NVYL82M7S3755118 | 76076 | Remi
LF76-76 | 2NVYL82M7S3755118 | 76076 | Richard L
LF76-76 | 2NVYL82M7S3755118 | 76076 | Stephane
LF76-77 | 2NVYL82M9S3755119 | 76077 | Daniel
LF76-77 | 2NVYL82M9S3755119 | 76077 | Gaetan 2
LF76-77 | 2NVYL82M9S3755119 | 76077 | Daniel2 | 8/25/2025 | 8/25/2025 | 8/26/2025 | 8/26/2025 | 8/27/2025 | 8/27/2025 | 8/27/2025 | 8/28/2025 | 8/28/2025 | 8/29/2025 | 8/29/2025 | 8/29/2025 | 8/30/2025 | 8/30/2025 | 8/30/2025 | 8/31/2025 | 8/31/2025 | 8/31/2025 | 9/2/2025 | 9/3/2025 | 9/4/2025 | 9/1/2025 | 9/3/2025 | 9/4/2025 |  |  |  |  | 9/1/2025
LF76-77 | 2NVYL82M9S3755119 | 76077 | Remi
LF76-77 | 2NVYL82M9S3755119 | 76077 | Stephane
LF76-77 | 2NVYL82M9S3755119 | 76077 | Richard L
LF76-78 | 2NVYL82M5S3755120 | 76078 | Daniel
LF76-78 | 2NVYL82M5S3755120 | 76078 | Gaetan 2
LF76-78 | 2NVYL82M5S3755120 | 76078 | Daniel2 | 8/25/2025 | 8/25/2025 | 8/26/2025 | 8/26/2025 | 8/27/2025 | 8/27/2025 | 8/28/2025 | 8/28/2025 | 8/29/2025 | 8/30/2025 | 8/29/2025 | 8/31/2025 | 9/1/2025 | 9/1/2025 | 9/1/2025 | 9/2/2025 | 9/2/2025 | 9/2/2025 | 9/3/2025 | 9/4/2025 |  | 9/3/2025 | 9/4/2025 | 9/4/2025 |  |  |  |  | 9/3/2025
LF76-78 | 2NVYL82M5S3755120 | 76078 | Richard L
LF76-78 | 2NVYL82M5S3755120 | 76078 | Remi
LF76-78 | 2NVYL82M5S3755120 | 76078 | Stephane
LF76-79 | 2NVYL82M7S3755121 | 76079 | Gaetan 2
LF76-79 | 2NVYL82M7S3755121 | 76079 | Daniel2 | 8/26/2025 | 8/26/2025 | 8/27/2025 | 8/27/2025 | 8/28/2025 | 8/28/2025 | 8/28/2025 | 8/29/2025 | 8/29/2025 | 8/29/2025 | 9/30/2025 | 10/1/2025 | 9/1/2025 | 9/1/2025 | 9/2/2025 | 9/2/2025 | 9/3/2025 | 9/3/2025 | 9/4/2025 |  |  | 9/4/2025 | [6 empty] | 9/4/2025
LF76-79 | 2NVYL82M7S3755121 | 76079 | Doyle Backup
LF76-79 | 2NVYL82M7S3755121 | 76079 | Remi
LF76-79 | 2NVYL82M7S3755121 | 76079 | Stephane
LF76-79 | 2NVYL82M7S3755121 | 76079 | Richard L
LF76-80 | 2NVYL82M1S3755132 | 76080 | Daniel
LF76-80 | 2NVYL82M1S3755132 | 76080 | Gaetan 2
LF76-80 | 2NVYL82M1S3755132 | 76080 | Daniel2 | 9/1/2025 | 9/1/2025 | 9/2/2025 | 9/10/2025 | 9/2/2025 | 9/3/2025 | 9/3/2025 | 9/3/2025 | 9/4/2025 | 9/4/2025 | 9/5/2025 | 9/5/2025 | 9/6/2025 | 9/6/2025 | 9/6/2025 | 9/7/2025 | 9/7/2025 | 9/7/2025 | 9/9/2025 | 9/10/2025 | 9/10/2025 | 9/8/2025 | 9/9/2025 | 9/10/2025 |  |  |  |  | 9/8/2025
LF76-80 | 2NVYL82M1S3755132 | 76080 | Remi
LF76-80 | 2NVYL82M1S3755132 | 76080 | Richard L
LF76-80 | 2NVYL82M1S3755132 | 76080 | Stephane
LF76-79 | 2NVYL82M7S3755121 | 76079 | Daniel
LF76-79 | 2NVYL82M7S3755121 | 76079 | Daniel2
LF76-79 | 2NVYL82M7S3755121 | 76079 | Gaetan 2
LF76-81 | 2NVYL82M3S3755133 | 76081 | Gaetan 2
LF76-81 | 2NVYL82M3S3755133 | 76081 | Daniel2
LF76-81 | 2NVYL82M3S3755133 | 76081 | Remi | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025 | 11/27/2025
LF76-81 | 2NVYL82M3S3755133 | 76081 | Stephane
LF76-81 | 2NVYL82M3S3755133 | 76081 | Richard L
LF76-82 | 2NVYL82M5S3755134 | 76082 | Gaetan 2
LF76-82 | 2NVYL82M5S3755134 | 76082 | Daniel2
LF76-82 | 2NVYL82M5S3755134 | 76082 | Remi
LF76-82 | 2NVYL82M5S3755134 | 76082 | Richard L
LF76-82 | 2NVYL82M5S3755134 | 76082 | Stephane
LF76-83 | 2NVYL82M7S3755135 | 76083 | Daniel
LF76-83 | 2NVYL82M7S3755135 | 76083 | Daniel2 | 9/1/2025 | 9/1/2025 | 9/1/2025 | 9/2/2025 | 9/2/2025 | 9/3/2025 | 9/3/2025 | 9/4/2025 | 9/4/2025 | 9/5/2025 | 9/5/2025 | 9/6/2025 | 9/6/2025 | 9/6/2025 | 9/7/2025 | 9/7/2025 | 9/8/2025 | 9/8/2025 | 9/10/2025 | 9/11/2025 | 9/11/2025 | 9/9/2025 | 9/10/2025 | 9/11/2025 |  |  |  |  | 9/9/2025
LF76-83 | 2NVYL82M7S3755135 | 76083 | Richard L
LF76-83 | 2NVYL82M7S3755135 | 76083 | Gaetan 2
LF76-83 | 2NVYL82M7S3755135 | 76083 | Remi
LF76-83 | 2NVYL82M7S3755135 | 76083 | Stephane
LF76-84 | 2NVYL82M9S3755136 | 76084 | Daniel
LF76-84 | 2NVYL82M9S3755136 | 76084 | Daniel2 | 9/2/2025 | 9/2/2025 | 9/3/2025 | 9/3/2025 | 9/4/2025 | 9/4/2025 | 9/5/2025 | 9/5/2025 | 9/6/2025 | 9/6/2025 | 9/6/2025 | 9/7/2025 | 9/7/2025 | 9/7/2025 | 9/8/2025 | 9/8/2025 | 9/9/2025 | 9/9/2025 | 9/10/2025 |  |  | 9/10/2025 | 9/11/2025 | [5 empty] | 9/9/2025
LF76-84 | 2NVYL82M9S3755136 | 76084 | Richard L
LF76-84 | 2NVYL82M9S3755136 | 76084 | Gaetan 2
LF76-84 | 2NVYL82M9S3755136 | 76084 | Remi
LF76-84 | 2NVYL82M9S3755136 | 76084 | Stephane
LF76-85 | 2NVYL82M0S3755137 | 76085 | Daniel
LF76-85 | 2NVYL82M0S3755137 | 76085 | Daniel2 | 9/2/2025 | 9/3/2025 | 9/3/2025 | 9/4/2025 | 9/4/2025 | 9/5/2025 | 9/5/2025 | 9/6/2025 | 9/6/2025 | 9/7/2025 | 9/7/2025 | 9/7/2025 | 9/8/2025 | 9/8/2025 | 9/9/2025 | 9/9/2025 | 9/10/2025 | 9/10/2025 | 9/11/2025 |  |  | 9/11/2025 | [6 empty] | 9/11/2025
LF76-85 | 2NVYL82M0S3755137 | 76085 | Gaetan 2
LF76-85 | 2NVYL82M0S3755137 | 76085 | Remi
LF76-85 | 2NVYL82M0S3755137 | 76085 | Stephane
lf76-86 | 2NVYL82M2S3755138 | 76086 | Daniel
lf76-86 | 2NVYL82M2S3755138 | 76086 | Daniel2
lf76-86 | 2NVYL82M2S3755138 | 76086 | Gaetan 2
lf76-86 | 2NVYL82M2S3755138 | 76086 | Richard L
lf76-86 | 2NVYL82M2S3755138 | 76086 | Remi
lf76-86 | 2NVYL82M2S3755138 | 76086 | Stephane
lf76-87 | 2NVYL82M4S3755139 | 76087 | Daniel
lf76-87 | 2NVYL82M4S3755139 | 76087 | Daniel2 | 9/18/2025 | 9/19/2025 | 9/19/2025 | 9/20/2025 | 9/20/2025 | 9/21/2025 | 9/21/2025 | 9/21/2025 | 9/22/2025 | 9/22/2025 | 9/23/2025 | 9/23/2025 | 9/24/2025 | 9/24/2025 | 9/25/2025 | 9/25/2025
lf76-87 | 2NVYL82M4S3755139 | 76087 | Gaetan 2
lf76-87 | 2NVYL82M4S3755139 | 76087 | Remi
lf76-87 | 2NVYL82M4S3755139 | 76087 | Stephane
LF76-88 | 2NVYL82M0S3755140 | 76088 | Daniel
LF76-88 | 2NVYL82M0S3755140 | 76088 | Daniel2
LF76-88 | 2NVYL82M0S3755140 | 76088 | Gaetan 2
LF76-88 | 2NVYL82M0S3755140 | 76088 | Remi
LF76-88 | 2NVYL82M0S3755140 | 76088 | Richard L
LF76-88 | 2NVYL82M0S3755140 | 76088 | Stephane
LF76-89 | 2NVYL82M0S3755154 | 76089 | Daniel
LF76-89 | 2NVYL82M0S3755154 | 76089 | Gaetan 2
LF76-89 | 2NVYL82M0S3755154 | 76089 | Remi
LF76-89 | 2NVYL82M0S3755154 | 76089 | Richard L
LF76-89 | 2NVYL82M0S3755154 | 76089 | Stephane
LF76-90 | 2NVYL82M2S3755155 | 76090 | Gaetan 2
LF76-90 | 2NVYL82M2S3755155 | 76090 | Remi
LF76-90 | 2NVYL82M2S3755155 | 76090 | Stephane
LF76-91 | 2NVYL82M4S3755156 | 76091 | Daniel2
LF76-91 | 2NVYL82M4S3755156 | 76091 | Richard L
LF76-91 | 2NVYL82M4S3755156 | 76091 | Remi
LF76-91 | 2NVYL82M4S3755156 | 76091 | Stephane
LF76-92 | 2NVYL82M6S3755157 | 76092 | Daniel2
LF76-92 | 2NVYL82M6S3755157 | 76092 | Richard L
LF76-92 | 2NVYL82M6S3755157 | 76092 | Remi
LF76-92 | 2NVYL82M6S3755157 | 76092 | Gaetan 2
LF76-92 | 2NVYL82M6S3755157 | 76092 | Stephane
LF76-93 | 2NVYL82M8S3755158 | 76093 | Daniel2 | 9/11/2025 | 9/12/2025 | 9/12/2025 | 9/13/2025 | 9/13/2025 | 9/13/2025 | 9/14/2025 | 9/14/2025 | 9/15/2025 | 9/15/2025 | 9/16/2025 | 9/16/2025 | 9/17/2025 | 9/17/2025 | 9/18/2025 | 9/19/2025 | 9/19/2025 | 9/20/2025 | 9/21/2025 | 9/22/2025 | 9/22/2025 | 9/21/2025 | 9/21/2025 | 9/22/2025 |  |  |  |  | 9/20/2025
LF76-93 | 2NVYL82M8S3755158 | 76093 | Richard L
LF76-93 | 2NVYL82M8S3755158 | 76093 | Remi
LF76-93 | 2NVYL82M8S3755158 | 76093 | Gaetan 2
LF76-93 | 2NVYL82M8S3755158 | 76093 | Stephane
LF76-94 | 2NVYL82MXS3755159 | 76094 | Daniel2 | 9/12/2025 | 9/12/2025 | 9/12/2025 | 9/13/2025 | 9/13/2025 | 9/14/2025 | 9/14/2025 | 9/14/2025 | 9/15/2025 | 9/15/2025 | 9/16/2025 | 9/16/2025 | 9/17/2025 | 9/17/2025 | 9/18/2025 | 9/18/2025 | 9/19/2025 | 9/19/2025 | 9/21/2025 | 9/21/2025 | 9/22/2025 | 9/20/2025 | 9/21/2025 | 9/22/2025 |  |  |  |  | 9/20/2025
LF76-94 | 2NVYL82MXS3755159 | 76094 | Richard L
LF76-94 | 2NVYL82MXS3755159 | 76094 | Remi
LF76-96 | 2NVYL82M6S3755160 | 76096 | Daniel2 | 9/15/2025 | 9/16/2025 | 9/16/2025 | 9/17/2025 | 9/17/2025 | 9/18/2025 | 9/18/2025 | 9/19/2025 | 9/19/2025 | 9/20/2025 | 9/20/2025 | 9/21/2025 | 9/21/2025 | 9/21/2025 | 9/21/2025 | 9/22/2025 | 9/22/2025
LF76-96 | 2NVYL82M6S3755160 | 76096 | Richard L
LF76-96 | 2NVYL82M6S3755160 | 76096 | Remi
LF76-96 | 2NVYL82M6S3755160 | 76096 | Gaetan 2
LF76-96 | 2NVYL82M6S3755160 | 76096 | Stephane
LF76-97 | 2NVYL82MXS3755162 | 76097 | Daniel2 | 9/16/2025 | 9/16/2025 | 9/16/2025 | 9/17/2025 | 9/17/2025 | 9/18/2025 | 9/18/2025 | 9/19/2025 | 9/19/2025 | 9/19/2025 | 9/20/2025 | 9/20/2025 | 9/21/2025 | 9/21/2025 | 9/22/2025 | 9/22/2025
LF76-97 | 2NVYL82MXS3755162 | 76097 | Richard L
LF76-97 | 2NVYL82MXS3755162 | 76097 | Remi
LF76-97 | 2NVYL82MXS3755162 | 76097 | Gaetan 2
LF76-97 | 2NVYL82MXS3755162 | 76097 | Stephane
LF76-98 | 2NVYL82M1S3755163 | 76098 | Daniel2 | 9/16/2025 | 9/16/2025 | 9/16/2025 | 9/17/2025 | 9/17/2025 | 9/18/2025 | 9/18/2025 | 9/19/2025 | 9/19/2025 | 9/20/2025 | 9/20/2025 | 9/21/2025 | 9/21/2025 | 9/21/2025 | 9/22/2025 | 9/22/2025
LF76-98 | 2NVYL82M1S3755163 | 76098 | Richard L
LF76-98 | 2NVYL82M1S3755163 | 76098 | Remi
LF76-98 | 2NVYL82M1S3755163 | 76098 | Gaetan 2
LF76-98 | 2NVYL82M1S3755163 | 76098 | Stephane
LF76-99 | 2NVYL82M3S3755164 | 76099 | Daniel2 | 9/16/2025 | 9/16/2025 | 9/17/2025 | 9/17/2025 | 9/17/2025 | 9/18/2025 | 9/18/2025 | 9/19/2025 | 9/19/2025 | 9/19/2025 | 9/20/2025 | 9/20/2025 | 9/21/2025 | 9/21/2025 | 9/22/2025 | 9/22/2025
LF76-99 | 2NVYL82M3S3755164 | 76099 | Richard L
LF76-99 | 2NVYL82M3S3755164 | 76099 | Remi
LF76-99 | 2NVYL82M3S3755164 | 76099 | Gaetan 2
LF76-99 | 2NVYL82M3S3755164 | 76099 | Stephane
LF76-100 | 2NVYL82M5S3755165 | 76100 | Daniel2 | 9/17/2025 | 9/17/2025 | 9/17/2025 | 9/18/2025 | 9/18/2025 | 9/19/2025 | 9/19/2025 | 9/20/2025 | 9/20/2025 | 9/21/2025 | 9/21/2025 | 9/22/2025 | 9/22/2025
LF76-100 | 2NVYL82M5S3755165 | 76100 | Richard L
LF76-100 | 2NVYL82M5S3755165 | 76100 | Gaetan 2
LF76-100 | 2NVYL82M5S3755165 | 76100 | Remi
LF76-100 | 2NVYL82M5S3755165 | 76100 | Stephane
LF76-102 | 2NVYL82M5S3755182 | 76102 | Daniel2 | 9/25/2025 | 9/25/2025 | 9/26/2025 | 9/26/2025 | 9/27/2025 | 9/27/2025 | 9/28/2025 | 9/28/2025 | 10/28/2025 | 9/29/2025 | 9/29/2025 | 9/30/2025 | 9/30/2025 | 9/30/2025 | 10/1/2025 | 10/1/2025 | 10/2/2025 | 10/2/2025 | 10/3/2025 |  |  | 10/3/2025 | 10/3/2025 | [5 empty] | 10/2/2025
LF76-102 | 2NVYL82M5S3755182 | 76102 | Gaetan 2
LF76-102 | 2NVYL82M5S3755182 | 76102 | Remi
LF76-102 | 2NVYL82M5S3755182 | 76102 | Richard L
LF76-102 | 2NVYL82M5S3755182 | 76102 | Stephane
LF76-103 | 2NVYL82M7S3755183 | 76103 | Daniel2 | 9/25/2025 | 9/25/2025 | 9/26/2025 | 9/26/2025 | 9/27/2025 | 9/27/2025 | 9/28/2025 | 9/28/2025 | 9/28/2025 | 9/29/2025 | 9/29/2025 | 9/30/2025 | 9/30/2025 | 10/1/2025 | 10/1/2025 | 10/2/2025 | 10/2/2025 | 10/2/2025 | 10/3/2025 |  |  | 10/3/2025 | [6 empty] | 10/3/2025
LF76-103 | 2NVYL82M7S3755183 | 76103 | Remi
LF76-103 | 2NVYL82M7S3755183 | 76103 | Richard L
LF76-103 | 2NVYL82M7S3755183 | 76103 | Stephane
LF76-103 | 2NVYL82M7S3755183 | 76103 | Gaetan 2
LF76-104 | 2NVYL82M9S3755184 | 76104 | Daniel2 | 9/25/2025 | 9/25/2025 | 9/26/2025 | 9/26/2025 | 9/27/2025 | 9/28/2025 | 9/28/2025 | 9/28/2025 | 10/29/2025 | 10/29/2025 | 9/30/2025 | 9/30/2025 | 10/1/2025 | 10/1/2025 | 10/2/2025 | 10/2/2025 | 10/3/2025 | 10/3/2025 | [10 empty] | 10/3/2025
LF76-104 | 2NVYL82M9S3755184 | 76104 | Gaetan 2 | [28 empty] | 10/7/2025
LF76-104 | 2NVYL82M9S3755184 | 76104 | Remi
LF76-104 | 2NVYL82M9S3755184 | 76104 | Richard L
LF76-104 | 2NVYL82M9S3755184 | 76104 | Stephane
LF76-105 | 2NVYL82M0S3755185 | 76105 | Daniel2 | 9/26/2025 | 9/26/2025 | 9/27/2025 | 9/27/2025 | 9/28/2025 | 9/28/2025 | 9/28/2025 | 9/29/2025 | 9/29/2025 | 9/30/2025 | 9/30/2025 | 10/1/2025 | 10/1/2025 | 10/2/2025 | 10/2/2025 | 10/3/2025 | 10/3/2025 | 10/3/2025
LF76-105 | 2NVYL82M0S3755185 | 76105 | Gaetan 2 | [28 empty] | 10/7/2025
LF76-105 | 2NVYL82M0S3755185 | 76105 | Remi
LF76-105 | 2NVYL82M0S3755185 | 76105 | Richard L
LF76-105 | 2NVYL82M0S3755185 | 76105 | Stephane
LF76-106 | 2NVYL82M2S3755186 | 76106 | Daniel2 | 9/26/2025 | 9/27/2025 | 9/27/2025 | 9/28/2025 | 9/28/2025 | 9/28/2025 | 9/29/2025 | 9/29/2025 | 9/30/2025 | 9/30/2025 | 10/1/2025 | 10/1/2025 | 10/2/2025 | 10/2/2025 | 10/2/2025 | 10/3/2025 | 10/3/2025
LF76-106 | 2NVYL82M2S3755186 | 76106 | Gaetan 2 | [28 empty] | 10/7/2025
LF76-106 | 2NVYL82M2S3755186 | 76106 | Remi
LF76-106 | 2NVYL82M2S3755186 | 76106 | Stephane
LF76-107 | 2NVYL82M4S3755187 | 76107 | Daniel2 | 9/27/2025 | 9/27/2025 | 9/28/2025 | 9/28/2025 | 9/28/2025 | 9/29/2025 | 9/29/2025 | 9/30/2025 | 9/30/2025 | 10/1/2025 | 10/1/2025 | 10/2/2025 | 10/2/2025 | 10/3/2025 | 10/3/2025 | 10/3/2025
LF76-107 | 2NVYL82M4S3755187 | 76107 | Gaetan 2 | [28 empty] | 10/7/2025
LF76-107 | 2NVYL82M4S3755187 | 76107 | Stephane
LF76-107 | 2NVYL82M4S3755187 | 76107 | Remi
LF76-107 | 2NVYL82M4S3755187 | 76107 | Richard L
LF76-108 | 2NVYL82M6S3755188 | 76108 | Daniel2 | 9/27/2025 | 9/27/2025 | 9/28/2025 | 9/28/2025 | 9/29/2025 | 9/29/2025 | 9/30/2025 | 9/30/2025 | 10/1/2025 | 10/1/2025 | 10/2/2025 | 10/2/2025 | 10/3/2025 | 10/3/2025 | 10/3/2025
LF76-108 | 2NVYL82M6S3755188 | 76108 | Gaetan 2 | [28 empty] | 10/7/2025
LF76-108 | 2NVYL82M6S3755188 | 76108 | Remi
LF76-108 | 2NVYL82M6S3755188 | 76108 | Richard L
LF76-108 | 2NVYL82M6S3755188 | 76108 | Stephane
LF76-109 | 2NVYL82M8S3755189 | 76109 | Daniel2 | 9/28/2025 | 9/28/2025 | 9/28/2025 | 9/29/2025 | 9/29/2025 | 9/30/2025 | 9/30/2025 | 10/1/2025 | 10/1/2025 | 10/2/2025 | 10/2/2025 | 10/3/2025 | 10/3/2025 | 10/3/2025
LF76-109 | 2NVYL82M8S3755189 | 76109 | Gaetan 2 | [28 empty] | 10/7/2025
LF76-109 | 2NVYL82M8S3755189 | 76109 | Remi
LF76-109 | 2NVYL82M8S3755189 | 76109 | Richard L
LF76-109 | 2NVYL82M8S3755189 | 76109 | Stephane
LF76-110 | 2NVYL82M4S3755190 | 76110 | Daniel2 | 9/28/2025 | 9/28/2025 | 9/29/2025 | 9/29/2025 | 9/30/2025 | 9/30/2025 | 10/1/2025 | 10/1/2025 | 10/2/2025 | 10/2/2025 | 10/3/2025 | 10/3/2025 | 10/3/2025
LF76-110 | 2NVYL82M4S3755190 | 76110 | Gaetan 2 | [28 empty] | 10/7/2025
LF76-110 | 2NVYL82M4S3755190 | 76110 | Remi
LF76-110 | 2NVYL82M4S3755190 | 76110 | Richard L
LF76-110 | 2NVYL82M4S3755190 | 76110 | Stephane
LF76-111 | 2NVYL82M6S3755191 | 76111 | Daniel2 | 9/28/2025 | 9/29/2025 | 9/29/2025 | 9/30/2025 | 9/30/2025 | 10/1/2025 | 10/1/2025 | 10/2/2025 | 10/2/2025 | 10/3/2025 | 10/3/2025 | 10/3/2025
LF76-111 | 2NVYL82M6S3755191 | 76111 | Gaetan 2 | [17 empty] | 10/7/2025 | [10 empty] | 10/7/2025
LF76-111 | 2NVYL82M6S3755191 | 76111 | Stephane
LF76-111 | 2NVYL82M6S3755191 | 76111 | Remi
LF76-111 | 2NVYL82M6S3755191 | 76111 | Richard L
LF76-112 | 2NVYL82M8S3755192 | 76112 | Daniel2 | 9/29/2025 | 9/30/2025 | 9/30/2025 | 10/1/2025 | 10/1/2025 | 10/2/2025 | 10/2/2025 | 10/3/2025 | 10/3/2025 | 10/3/2025
LF76-112 | 2NVYL82M8S3755192 | 76112 | Gaetan 2 | [16 empty] | 10/7/2025 | 10/7/2025 | [10 empty] | 10/7/2025
LF76-112 | 2NVYL82M8S3755192 | 76112 | Stephane
LF76-112 | 2NVYL82M8S3755192 | 76112 | Remi
LF76-112 | 2NVYL82M8S3755192 | 76112 | Richard L
LF76-113 | 2NVYL82M6S3755207 | 76113 | Gaetan 2 | 10/8/2025 | 10/8/2025 | 10/9/2025 | 10/9/2025 | 10/9/2025 | 10/16/2025 | [5 empty] | 10/14/2025 | 10/14/2025 | 10/15/2025 | 10/15/2025 | 10/15/2025 | 10/16/2025 | 10/16/2025 | [10 empty] | 10/17/2025
LF76-113 | 2NVYL82M6S3755207 | 76113 | Remi
LF76-113 | 2NVYL82M6S3755207 | 76113 | Richard L
LF76-113 | 2NVYL82M6S3755207 | 76113 | Stephane
LF76-114 | 2NVYL82M8S3755208 | 76114 | Gaetan 2 | [10 empty] | 10/14/2025 | 10/14/2025 | 10/14/2025 | 10/15/2025 | 10/15/2025 | 10/15/2025 | 10/16/2025 | 10/16/2025 | [10 empty] | 10/17/2025
LF76-114 | 2NVYL82M8S3755208 | 76114 | Remi
LF76-114 | 2NVYL82M8S3755208 | 76114 | Stephane
LF76-115 | 2NVYL82MXS3755209 | 76115 | Gaetan 2 | [11 empty] | 10/14/2025 | 10/14/2025 | 10/14/2025 | 10/16/2025 | 10/16/2025 | 10/16/2025 | 10/16/2025 | [10 empty] | 10/17/2025
LF76-115 | 2NVYL82MXS3755209 | 76115 | Remi
LF76-115 | 2NVYL82MXS3755209 | 76115 | Richard L
LF76-115 | 2NVYL82MXS3755209 | 76115 | Stephane
LF76-116 | 2NVYL82M6S3755210 | 76116 | Gaetan 2 | [8 empty] | 10/14/2025 | 10/14/2025 | 10/14/2025 | 10/15/2025 | 10/15/2025 | 10/17/2025 | 10/17/2025 | 10/17/2025 | 10/17/2025 | 10/17/2025 | [10 empty] | 10/17/2025
LF76-116 | 2NVYL82M6S3755210 | 76116 | Remi
LF76-116 | 2NVYL82M6S3755210 | 76116 | Stephane
LF76-117 | 2NVYL82M8S3755211 | 76117 | Gaetan 2 | [7 empty] | 10/14/2025 | 10/14/2025 | 10/14/2025 | 10/15/2025 | 10/15/2025 | 10/15/2025 | 10/16/2025 | 10/16/2025 | 10/16/2025 | 10/16/2025 | 10/16/2025 | [10 empty] | 10/17/2025
LF76-117 | 2NVYL82M8S3755211 | 76117 | Stephane
LF76-117 | 2NVYL82M8S3755211 | 76117 | Remi
LF76-118 | 2NVYL82MXS3755212 | 76118 | Gaetan 2 | [6 empty] | 10/14/2025 | 10/14/2025 | 10/14/2025 | 10/15/2025 | 10/15/2025 | 10/15/2025 | 10/16/2025 | 10/16/2025 | 10/16/2025 | 10/16/2025 | 10/16/2025 | 10/17/2025 | [10 empty] | 10/17/2025
LF76-118 | 2NVYL82MXS3755212 | 76118 | Remi
LF76-118 | 2NVYL82MXS3755212 | 76118 | Richard L
LF76-118 | 2NVYL82MXS3755212 | 76118 | Stephane
LF76-119 | 2NVYL82M1S3755213 | 76119 | Gaetan 2 | [5 empty] | 10/14/2025 | 10/14/2025 | 10/14/2025 | 10/15/2025 | 10/15/2025 | 10/15/2025 | 10/16/2025 | 10/16/2025 | 10/16/2025 | 10/16/2025 | 10/16/2025 | 10/20/2025 | 10/20/2025 | [10 empty] | 10/20/2025
LF76-119 | 2NVYL82M1S3755213 | 76119 | Remi
LF76-119 | 2NVYL82M1S3755213 | 76119 | Stephane
LF76-119 | 2NVYL82M1S3755213 | 76119 | Daniel2
LF76-120 | 2NVYL82M3S3755214 | 76120 | Gaetan 2 | [6 empty] | 10/15/2025 | 10/15/2025 | 10/15/2025 | 10/16/2025 | 10/16/2025 | 10/16/2025 | 10/16/2025 | 10/16/2025 | 10/16/2025 | 10/17/2025 | 10/17/2025 | 10/17/2025 | [10 empty] | 10/20/2025
LF76-121 | 2NVYL82M5S3755215 | 76121 | Gaetan 2 | [5 empty] | 10/15/2025 | 10/15/2025 | 10/15/2025 | 10/16/2025 | 10/16/2025 | 10/16/2025 | 10/16/2025 | 10/16/2025 | 10/16/2025 | 10/17/2025 | 10/17/2025 | 10/17/2025 | 10/20/2025 | [10 empty] | 10/20/2025
LF76-121 | 2NVYL82M5S3755215 | 76121 | Remi
LF76-121 | 2NVYL82M5S3755215 | 76121 | Stephane
LF76-122 | 2NVYL82M8S3755225 | 76122 | Daniel2 | 10/16/2025 | 10/16/2025 | 10/17/2025 | 10/17/2025 | 10/18/2025 | 10/18/2025 | 10/19/2025 | 10/19/2025 | 10/19/2025 | 10/20/2025 | 10/21/2025 | 10/21/2025 | 10/21/2025 | 10/22/2025 | 10/22/2025 | 10/22/2025 | 10/23/2025 | 10/23/2025 | [10 empty] | 10/23/2025
LF76-122 | 2NVYL82M8S3755225 | 76122 | Gaetan 2
LF76-122 | 2NVYL82M8S3755225 | 76122 | Remi
LF76-122 | 2NVYL82M8S3755225 | 76122 | Stephane
LF76-123 | 2NVYL82MXS3755226 | 76123 | Daniel2 | 10/17/2025 | 10/17/2025 | 10/18/2025 | 10/18/2025 | 10/18/2025 | 10/19/2025 | 10/19/2025 | 10/20/2025 | 10/20/2025 | 10/21/2025 | 10/21/2025 | 10/21/2025 | 10/22/2025 | 10/22/2025 | 10/22/2025 | 10/23/2025 | 10/23/2025 | 10/23/2025
LF76-123 | 2NVYL82MXS3755226 | 76123 | Gaetan 2
LF76-123 | 2NVYL82MXS3755226 | 76123 | Richard L
LF76-123 | 2NVYL82MXS3755226 | 76123 | Stephane
LF76-123 | 2NVYL82MXS3755226 | 76123 | Remi Test
LF76-123 | 2NVYL82MXS3755226 | 76123 | Remi
LF76-124 | 2NVYL82M1S3755227 | 76124 | Daniel2 | 10/17/2025 | 10/18/2025 | 10/18/2025 | 10/19/2025 | 10/19/2025 | 10/19/2025 | 10/19/2025 | 10/20/2025 | 10/21/2025 | 10/21/2025 | 10/21/2025 | 10/22/2025 | 10/22/2025 | 10/22/2025 | 10/22/2025 | 10/23/2025 | 10/23/2025
LF76-124 | 2NVYL82M1S3755227 | 76124 | Gaetan 2
LF76-124 | 2NVYL82M1S3755227 | 76124 | Remi
LF76-124 | 2NVYL82M1S3755227 | 76124 | Richard L
LF76-124 | 2NVYL82M1S3755227 | 76124 | Stephane
LF76-125 | 2NVYL82M3S3755228 | 76125 | Daniel2 | 10/18/2025 | 10/18/2025 | 10/19/2025 | 10/19/2025 | 10/19/2025 | 10/20/2025 | 10/20/2025 | 10/21/2025 | 10/21/2025 | 10/21/2025 | 10/22/2025 | 10/22/2025 | 10/22/2025 | 10/23/2025 | 10/23/2025 | 10/23/2025
LF76-125 | 2NVYL82M3S3755228 | 76125 | Remi
LF76-125 | 2NVYL82M3S3755228 | 76125 | Richard L
LF76-125 | 2NVYL82M3S3755228 | 76125 | Stephane
LF76-126 | 2NVYL82M5S3755229 | 76126 | Daniel2 | 10/18/2025 | 10/18/2025 | 10/19/2025 | 10/19/2025 | 10/19/2025 | 10/20/2025 | 10/21/2025 | 10/21/2025 | 10/21/2025 | 10/21/2025 | 10/22/2025 | 10/22/2025 | 10/23/2025 | 10/23/2025 | 10/23/2025
LF76-127 | 2NVYL82M1S3755230 | 76127 | Daniel2 | 10/19/2025 | 10/19/2025 | 10/19/2025 | 10/20/2025 | 10/20/2025 | 10/20/2025 | 10/21/2025 | 10/21/2025 | 10/21/2025 | 10/22/2025 | 10/22/2025 | 10/22/2025 | 10/23/2025 | 10/23/2025 | 10/23/2025 | 10/24/2025 | 10/24/2025 | 10/25/2025 | 10/26/2025 | 10/27/2025 | 10/27/2025 | 10/26/2025 | 10/26/2025 | 10/27/2025 |  |  |  |  | 10/25/2025
LF76-127 | 2NVYL82M1S3755230 | 76127 | Gaetan 2
LF76-127 | 2NVYL82M1S3755230 | 76127 | Remi
LF76-127 | 2NVYL82M1S3755230 | 76127 | Richard L
LF76-127 | 2NVYL82M1S3755230 | 76127 | Stephane
LF76-128 | 2NVYL82M3S3755231 | 76128 | Daniel2 | 10/19/2025 | 10/19/2025 | 10/19/2025 | 10/20/2025 | 10/20/2025 | 10/20/2025 | 10/21/2025 | 10/21/2025 | 10/22/2025 | 10/22/2025 | 10/22/2025 | 10/23/2025 | 10/23/2025 | 10/23/2025 | 10/24/2025 | 10/24/2025 | 10/25/2025 | 10/25/2025 | 10/27/2025 | 10/27/2025 |  | 10/26/2025 | 10/27/2025 | [5 empty] | 10/26/2025
LF76-129 | 2NVYL82M5S3755232 | 76129 | Daniel2 | 10/20/2025 | 10/20/2025 | 10/20/2025 | 10/21/2025 | 10/21/2025 | 10/21/2025 | 10/21/2025 | 10/22/2025 | 10/22/2025 | 10/22/2025 | 10/22/2025 | 10/23/2025 | 10/23/2025 | 10/24/2025 | 10/24/2025 | 10/25/2025 | 10/26/2025 | 10/26/2025 | 10/27/2025 |  |  | 10/27/2025 | 10/27/2025
LF76-129 | 2NVYL82M5S3755232 | 76129 | Gaetan 2
LF76-129 | 2NVYL82M5S3755232 | 76129 | Remi
LF76-129 | 2NVYL82M5S3755232 | 76129 | Richard L
LF76-129 | 2NVYL82M5S3755232 | 76129 | Stephane
LF76-130 | 2NVYL82M7S3755233 | 76130 | Daniel2 | 10/20/2025 | 10/20/2025 | 10/21/2025 | 10/21/2025 | 10/21/2025 | 10/22/2025 | 10/22/2025 | 10/22/2025 | 10/23/2025 | 10/23/2025 | 10/23/2025 | 10/24/2025 | 10/25/2025 | 10/26/2025 | 10/26/2025 | 10/27/2025 | 10/27/2025 | 10/27/2025
LF76-131 | 2NVYL82M9S3755234 | 76131 | Daniel2 | 10/20/2025 | 10/20/2025 | 10/21/2025 | 10/21/2025 | 10/22/2025 | 10/22/2025 | 10/22/2025 | 10/23/2025 | 10/23/2025 | 10/23/2025 | 10/24/2025 | 10/24/2025 | 10/25/2025 | 10/25/2025 | 10/26/2025 | 10/26/2025 | 10/27/2025
LF76-132 | 2NVYL82M0S3755235 | 76132 | Daniel2 | 10/21/2025 | 10/21/2025 | 10/21/2025 | 10/22/2025 | 10/22/2025 | 10/22/2025 | 10/23/2025 | 10/23/2025 | 10/23/2025 | 10/24/2025 | 10/25/2025 | 10/25/2025 | 10/26/2025 | 10/26/2025 | 10/27/2025 | 10/27/2025
LF76-133 | 2NVYL82M2S3755236 | 76133 | Daniel2 | 10/20/2025 | 10/20/2025 | 10/20/2025 | 10/20/2025 | 10/21/2025 | 10/21/2025 | 10/22/2025 | 10/22/2025 | 10/23/2025 | 10/24/2025 | 10/23/2025 | 10/26/2025 | 10/26/2025 | 10/27/2025 | 10/27/2025
LF76-134 | 2NVYL82M4S3755237 | 76134 | Daniel2 | 10/20/2025 | 10/20/2025 | 10/21/2025 | 10/21/2025 | 10/22/2025 | 10/22/2025 | 10/23/2025 | 10/24/2025 | 10/25/2025 | 10/25/2025 | 10/26/2025 | 10/26/2025 | 10/27/2025 | 10/27/2025
LF76-95 | 2NVYL82M6S3755160 | 76095 | Daniel2
LF76-95 | 2NVYL82M6S3755160 | 76095 | Gaetan 2
LF76-95 | 2NVYL82M6S3755160 | 76095 | Remi
LF76-95 | 2NVYL82M6S3755160 | 76095 | Stephane
LF76-95 | 2NVYL82M6S3755160 | 76095 | Richard L
LF76-101 | 2NVYL82M3S3755181 | 76101 | Daniel2 | 9/23/2025 | 9/24/2025 | 9/25/2025 | 9/25/2025 | 9/26/2025 | 9/26/2025 | 9/27/2025 | 9/27/2025 | 9/28/2025 | 9/28/2025 | 9/28/2025 | 9/29/2025 | 9/29/2025 | 9/30/2025 | 9/30/2025 | 10/1/2025 | 10/1/2025 | 10/2/2025 | 9/30/2025 | 10/1/2025 | 10/2/2025 | 9/29/2025 | 9/30/2025 | 10/1/2025 | 10/2/2025 | 10/3/2025 | 10/3/2025 | 10/3/2025 | 10/2/2025
LF76-101 | 2NVYL82M3S3755181 | 76101 | Gaetan 2
LF76-101 | 2NVYL82M3S3755181 | 76101 | Remi
LF76-101 | 2NVYL82M3S3755181 | 76101 | Richard L
LF76-101 | 2NVYL82M3S3755181 | 76101 | Stephane